STAT627

Final Project Proposal

Members: Ana Paula Miranda, Drew McPherson

- Project Title

Predicting Outcomes in Apprenticeship

- Group Members

| Member | Course |
| --- | --- |
| Ana Paula Miranda | STAT 627 |
| Drew McPherson | STAT 627 |

- Topic

For this effort, we will seek to predict apprentice outcomes (wage, completion status) based on apprentice and apprenticeship characteristics.

- Questions of Interest

  - Regression

    - What do we predict an apprentice’s exit wage will be based on the apprentice’s occupational group, age, education level, race, and competition status?

  - Classification

    - Do we predict an apprentice will complete their apprenticeship based on the apprentice’s occupational group, age, education level, race, and training model?

- Planned Approach

  - Literature Review

    - U.S. Department of Labor, Clearinghouse for Labor Evaluation and Research. (2024, June). Registered apprenticeship and work-based learning: Research synthesis (Revised Oct. 31, 2024). https://clear.dol.gov/sites/default/files/ResearchSynthesis_ApprenticeshipWBL_2024-06_Revised.10.31.24.pdf

    - Copson, E., Kappil, T., Gardiner, K., Clarkwest, A., Engle, H., Trutko, A., Trutko, J., Glosser, A., Webster, R., Kuehn, D., Lerman, R., & Shakesprere, J. (2021). Implementing Registered Apprenticeship Programs: Experiences of 10 American Apprenticeship Initiative Grantees. Prepared for the U.S. Department of Labor, Employment and Training Administration. Rockville, MD: Abt Associates.

    - Butrica, Barbara A., Jones, Elizabeth, Rosenberg, Linda, Sattar, Samina, Sotelo, Veronica. A Review of the Literature on Registered Apprenticeships - Evaluating Registered Apprenticeship Initiatives. Copyright © August 2023. Urban Institute. https://www.dol.gov/sites/dolgov/files/ETA/publications/ETAOP_2023_17_ERAI_Literature_Review_Final.pdf

  - Data Assessment

    - We will use the U.S. Department of Labor’s public dataset, which is created using the Registered Apprenticeship Partner Information Database System (RAPIDS).

    - This dataset was provided by request on 6/22/25.

    - The apprentice dataset consists of 3,708,450 observations across 77 variables. We will use a subset of this data.

    - Variables consist of integers, floats, and factors. A number of variables contain codes which will have to be converted for effective usage.

- Planned Methods

  - Expected Methods

    - We will explore a number of different ML methods for achieving our objectives.

    - Regression

      - Linear Regression

      - LASSO Regression

      - Ridge Regression

      - PCR Regression

      - PLS Regression

    - Classification

      - KNN

      - Logistic Regression

      - LDA

      - QDA

      - Tree-based Methods

    - Performance

      - LOOCV

      - K-Fold CV

  - Method for Assessing Multicollinearity

    - Primary Component Analysis

    - VIF

    - Variable Selection

    - Shrinkage

    - Stepwise Variable Selection

  - Methods for Model Comparison

    - AIC

    - BIC

    - R-Squared

    - Mallows Cp

    - MSE

    - RMSE

    - ANOVA

  - Identification of Potential Ethical Concerns

    - There are no immediate ethical concerns springing from the data. The data has already been anonymized and does not appear to contain enough information to allow for the identification of individuals.

    - Moreover, the data is publicly available to anyone who requests it.

    - There may be ethical concerns related to creating models predicting apprenticeship program completion based on demographic characteristics. These conclusions may lead to discrimination if businesses choose to stop hiring apprentices with lower expected completion rates.

    - However, this analysis could also be valuable in identifying obstacles to equity across different demographic characteristics, which would enable better targeted efforts to equalize completion rates across demographic groups.

    - We will mitigate our risks by ensuring that we include sufficient predictors to identify the factors beyond demographics (e.g. occupation, education level, age at start) that may contribute to this.

  - Risk Assessment and Mitigation

    - There are potential issues related to data quality. Data is collected from employers and reported “as is”. Therefore, there is potential for significant outliers springing from poor data quality. We will conduct exploratory data analysis for our predictors and target variables to identify and address any potential issues before we begin model evaluation.

- Deliverable

The final poster will contain an analysis of both research questions. We will detail the following elements:

- The results from exploratory data analysis

- Steps that were taken to transform/clean the dataset

- Feature development

- Model selection and approach

- Result validation and model refinement

- Description of final model

- Inference from final model

- Schedule and Hours

| Week | Task | Hours | Responsible |
| --- | --- | --- | --- |
| 10 | Project Plan Development | 4 | Drew/Ana |
| 11 | Initial data cleaning and refinement | 4 | Drew |
| 11 | Regression feature development and refinement | 4 | Ana |
| 11 | Classification feature development and refinement | 4 | Drew |
| 11 | Literature Review 1 | 4 | Drew |
| 11 | Literature Review 2 | 4 | Ana |
| 12 | Regression model selection | 6 | Ana |
| 12 | Regression model implementation | 4 | Ana |
| 12 | Regression model validation | 4 | Ana |
| 12 | Classification model selection | 6 | Drew |
| 12 | Classification model implementation | 4 | Drew |
| 12 | Classification model validation | 4 | Drew |
| 13 | Regression final model & findings | 2 | Ana |
| 13 | Classification final model & findings | 2 | Drew |
| 13 | Poster development | 8 | Ana/Drew |
| 14 | Presentation development | 8 | Ana/Drew |

- Group Member Responsibilities

| Member | Responsibility |
| --- | --- |
| Ana Paula Miranda | Regression Modeling |
| Drew McPherson | Classification Modeling |

- Summary

We will conduct a project titled “Predicting Outcomes in Apprenticeship.” The goal is to predict key apprenticeship outcomes – specifically, exit wage (regression) and completion status (classification) – using demographic and program characteristics such as occupational group, age, education, race, and training model.

We will utilize data from the U.S. Department of Labor’s Registered Apprenticeship Partner Information Database System (RAPIDS), a public dataset with over 3.7 million observations and 77 variables. We will subset the data, clean and recode categorical variables, and handle potential data quality and outlier issues.

We will evaluate the usage of K-Nearnest Neighbor (KNN), Logistic Regression, Ridge/Lasso, PCA, AIC/BIC and other methods for model comparison and assessment of multicollinearity. Ethical and data integrity considerations—such as representativeness, bias, and fairness—will be explicitly addressed.

The final deliverable will be a poster summarizing data cleaning, feature engineering, model development, validation, and final results for both regression and classification analyses.

Ana Paula will lead the regression modeling, while Drew McPherson will lead the classification modeling. Both will jointly prepare the poster and presentation, following a structured four-week schedule covering cleaning, modeling, validation, and final reporting.